## Product Backlog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | W2H/US1 | Site Member | Register Myself Using Mail Id & Mobile Number | I Can Receive A Confirmation/Verification Mail | 1
1 | W2H/US1 | Site Member | Receive A Confirmation Mail | I Can Access The Site | 1
1 | W2H/US1 | Site Member | Login Into The System Using Mail Id And Password | I Can View/Edit My Profile | 1
1 | W2H/US1 | Site Member | Modify The Account Password | I Can Keep My Account Secure | 1
1 | W2H/US1 | Site Member | Search For The Property With Area | I Can See/View List Property In Desired Area | 2
1 | W2H/US1 | Site Member | Search For The Property With Landmark | I Can See/View List Property In Desired Landmark | 2
1 | W2H/US1 | Site Member | Search For The Property Using Name Of Building/Township | I Can See/View List Property In Desired Building/Township | 2
1 | W2H/US1 | Site Member | See The Picture Of the Property | I Don't Have to Visit The Site Personally | 2
1 | W2H/US1 | Site Member | See The Popular Places/ Landmark/ Public Facilities Near By The Property | I Can Look For My Future Convenience | 2
1 | W2H/US1 | Site Member | See Rent/Purchase-Rate Of The Property | I Can Choose Property According To My Budget | 2
1 | W2H/US1 | Site Member | Fitler The Type Of Property (Flat/Pent House/Villa/Apartment/Builder Flats) | I Can View Only My Desired Type Of Property | 2
1 | W2H/US1 | Site Member | Fitler The Budget Of Property | I Can View Only View The Property In My Budget | 2
1 | W2H/US1 | Site Member | Fitler The Choose Area Of Property | I Can View Only Desired Property | 2
1 | W2H/US1 | Site Member | Contact The Concern Person For The Desired Property | I Can Proceed Furthur In Order To Book The Property | 4
1 | W2H/US1 | Site Member | Get The Response After Contacting The Concern Person | I Can Don't Have To Take Follow-ups | 4
| W2H/US1 | Site Member | Receive Notification Of Newly Added Property In My Interested Area. | I Can Have More Options In My Interseted Area. | 4
| W2H/US1 | Site Member | Contact To Customer Care | I Can Get Resolution For My Problem. | 4
| W2H/US1 | Site Member | See the Popular Properties | I Can Get Suggestions For Choosing a Better Property | 4
| W2H/US1 | Site Member | Give Feedback/Suggestions | The Way Of Working Of The Company Can Be Improved | 3
| W2H/US1 | Site Member | View My Past Activities On Website | I Can Keep A Check On My Activities | 3
| W2H/US1 | Site Member | Select the Property Constraint i.e. For Rent/Purchase | I Can View The Desired Property | 3
| W2H/US2 | Admin | Login Into The System Using Id And Password | I Can Access Admin Portal of The Website | 1
| W2H/US2 | Admin | Modify The Account Password | I Can Keep My Account Secure | 1
| W2H/US2 | Admin | Add New Property To DB | It can Be Displayed To The Website Users | 2
| W2H/US2 | Admin | Remove a Propery | It Won't Be Displayed To The Website Users Anymore | 2
| W2H/US2 | Admin | Check Number Of Registered Users On Website | I Can Keep Reocrd Of Users | 2
| W2H/US2 | Admin | Add a New User | I Can Have Flexibity With Users Management | 2
| W2H/US2 | Admin | I Can Remove A User | I Can Have Flexibity With Users Management | 2
| W2H/US2 | Admin | Add A New Owner/Agent To The Website | I Can Have Facility To Add A New Onwer/ Agent | 4
| W2H/US2 | Admin | View The Queries Of Customer | Provide Serivce To The Customer | 4
| W2H/US2 | Admin | View The FeedBack And Suggestions Of Customer | I Can Improve The Working Of System | 4
| W2H/US2 | Admin | To Edit USER/OWNER | I Can Make Changes In Case If An Error Occurs At Users/Owners End | 4
| W2H/US3 | Agent/Owner | Login Into The System Using Mail Id And Password | I Can View/Edit My Profile | 1
| W2H/US3 | Agent/Owner | Modify The Account Password | I Can Keep My Account Secure | 1
| W2H/US3 | Agent/Owner | View All The Listed Properties | I Can Track All The Listed Properties | 2
| W2H/US3 | Agent/Owner | Add A New Property | I Can Work Plan My Lectures | 2
| W2H/US3 | Agent/Owner | Modify The Account Password | I Can Keep My Account Secure | 2
| W2H/US3 | Agent/Owner | Get Notification On Email Whenever A Customer Tried to Contact Me | I Can Know The Customer is Tring To Reach Me | 4
| W2H/US3 | Agent/Owner | Get The Details Of User Who Tries To Contact Me | I Can Revert Back To The Customer | 4
| W2H/US3 | Agent/Owner | Make Any Change In Previous Listed Properties | I Can Provide Updated Information | 4
| W2H/US3 | Agent/Owner | Remove A New Property | I Can Delete The Property That Is Sold Or Rented. | 4
| W2H/US4 | DBA | Fire Insert Queries | I Can Insert New Records In The Database | 1
| W2H/US4 | DBA | Fire Select Queries | I Can View The Records | 1
| W2H/US4 | DBA | Fire Update Queries | I Can Keep The Database Updated | 1
| W2H/US4 | DBA | Fire Delete Queries | I Can Remove Unwanted Or Faulty Data | 1
| W2H/US4 | DBA | Take Backup | I Can Save The Old Records In The Database For Future Use | 3
| W2H/US4 | DBA | Delete Backup | I Can Delete The Records Which Is Not Needed Any More | 3
| W2H/US4 | DBA | Update Schema Design(If Required) | I Can Keep The DB Advanced & Upgraded | 2

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Property Listing>
SB1/US1 | Site Member | SB1/D1/T1 | Register Myself Using Mail Id & Mobile Number
|  | SB1/D1/T2 | Receive A Confirmation Mail
|  | SB1/D1/T3 | Login Into The System Using Mail Id And Password
|  | SB1/D1/T4 | Modify The Account Password
SB1/US2 | Admin | SB1/D1/T7 | Login Into The System Using Id And Password
|  | SB1/D1/T8 | Modify The Account Password
SB!/US3 | Agent/Owner | SB1/D1/T12 | Login Into The System Using Mail Id And Password
|  | SB1/D1/T13 | Modify The Account Password
SB1/US4 | DBA | SB1/D4/T1 | Fire Insert Queries
|  | SB1/D4/T2 | Fire Select Queries
|  | SB1/D4/T3 | Fire Update Queries
|  | SB1/D4/T4 | Fire Delete Queries

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 180 | Tasks
2018-09-12 | 120 | 180
2018-09-11 | 80 | 180
2018-09-14 | 56 | 180
2018-09-16 | 15 | 180
2018-09-18 | 5 | 180
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Property Listing>
SB2/US1 | Site Member | SB2/T1 | Search For The Property With Area
|  | SB2/T2 | Search For The Property With Landmark
|  | SB2/T3 | Search For The Property Using Name Of Building/Township
|  | SB2/T4 | See The Picture Of the Property
|  | SB2/T5 | See The Popular Places/ Landmark/ Public Facilities Near By The Property
|  | SB2/T6 | See Rent/Purchase-Rate Of The Property
|  | SB2/T7 | Fitler The Type Of Property (Flat/Pent House/Villa/Apartment/Builder Flats)
|  | SB2/T8 | Fitler The Budget Of Property
|  | SB2/T9 | Fitler The Choose Area Of Property
SB2/US2 | Admin | SB2/T10 | Add New Property To DB
|  | SB2/T11 | Remove a Propery
|  | SB2/T12 | Check Number Of Registered Users On Website
|  | SB2/T13 | Add a New User
|  | SB2/T14 | I Can Remove A User
SB2/US3 | Agent/Owner | SB2/T15 | View All The Listed Properties
|  | SB2/T16 | Add A New Property
|  | SB2/T17 | Modify The Account Password
SB2/US4 | DBA | SB2/T18 | Update Schema Design(If Required)

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Property Listing>
SB3/US1 | Site Member | SB3/T1 | Give Feedback/Suggestions
|  | SB3/T2 | View My Past Activities On Website
|  | SB3/T3 | Select the Property Constraint i.e. For Rent/Purchase
SB3/US1 | DBA | SB3/T4 | Take Backup
|  | SB3/T5 | Delete Backup

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Property Listing>
SB4/US1 | Site Members | SB4/T1 | Get Notification On Email Whenever A Customer Tried to Contact Me
|  | SB4/T2 | Get The Details Of User Who Tries To Contact Me
|  | SB4/T3 | Make Any Change In Previous Listed Properties
|  | SB4/T4 | Remove A New Property
SB4/US2 | Admin | SB4/T5 | Add A New Owner/Agent To The Website
|  | SB4/T6 | View The Queries Of Customer
|  | SB4/T7 | View The FeedBack And Suggestions Of Customer
|  | SB4/T8 | To Edit USER/OWNER
SB4/US3 | Site Members | SB4/T9 | Contact The Concern Person For The Desired Property
|  | SB4/T10 | Get The Response After Contacting The Concern Person
|  | SB4/T11 | Receive Notification Of Newly Added Property In My Interested Area.
|  | SB4/T12 | Contact To Customer Care
|  | SB4/T13 | See the Popular Properties

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days